## DrillingSummary
WellName | Date | Depth(m) | Hole Size(in) | Days | Summery | Event | Z (m)
WellA | 2019-08-27 | 19 | 36 | 1 | WAIT ON CLIENT WHILE RIG READY TO SPUD TILL 16:00 O CLOCK. SPUD THE RIG & START DRLG FORMATION W/ 26" R.BIT& BHA#1 TO 19 M TILL M.N. | Spud Rig | -19
WellA | 2019-08-28 | 87 | 36 | 2 | CONT. DRLG FORM. W/ 26" R.BIT#1 & 26" S.STAB @20 M F/ 19 TO 86 M W/ NL-NG WHILE RUN TOTCO-MACHINE @ 52 M, INC.: 0.1 DEG TILL M.N. |  | -87
WellA | 2019-08-29 | 107 | 36 | 3 | CONT. DRLG FORM. F/87 TO 107 M (TD), PUMP HI-VIS PILL & CLEAN THE WELL, RUN TOTCO @ 103 M, INC.: 0.25 DEG, POOH TO SURF., M/U 36" H.OPENER & RIH TO 15M, START ENLARGING F/ 13.7 TO 28 M W/ NL-NG TILL M.N. | Start Enlargement | -107
WellA | 2019-08-30 | 107 | 36 | 4 | CONT. ENLARGING THE WELL F/ 28 TO 48 M W/ NL-NG, POOH TO SURF. TO CHECK BIT & HOLE OPENER, OK. RIH TO 48 M, CONT. ENLARGING THE WELL F/ 48 TO 64 M W/ NL-NG TILL M.N. |  | -107
WellA | 2019-08-31 | 107 | 36 | 5 | CONT. ENLARGING THE WELL F/ 64 TO 100 M W/ NL-NG TILL M.N. |  | -107
WellA | 2019-09-01 | 107 | 36 | 6 | CONT. ENLARGING WELL TO 107 M, PUMP HI-VIS PILL & CLEAN THE WELL. POOH TO SURF & RUN BACK TO 107M AS COND. TRIP, PUMP HI-VIS PILL & CLEAN THE WELL. SPOT 250 BBL HI-VIS PILL. POOH TO SURF. R/UP CSG EQUIP. RIH 6 JTs 30" CSG TO 71M TILL M.N. | Finish Engargement | -107
WellA | 2019-09-02 | 107 | 36 | 7 | CONT. RIH 3 JTs (TOTALLY 9 JTs) 30" CSG TO 105M. PERFORM CMT JOB W/ STINGER. W.O.C FOR 5 HRs TO GET HARD. ROUGH CUT 42" CONDUCTOR PIPE & 30" CSG IN PROGRESS TILL M.N. | Cementing 30" CSG | -107
WellA | 2019-09-03 | 107 | 36 | 8 | ROUGH CUT 42" C. PIPE & 30" CSG, N/UP 30" D.SPOOL & 30" HI-DRILL (1 K), RIH W/ 26" R.BIT#1RR2 & BHA#3 TO 88 M, TEST 30" HI-DRILL, OK. WORK ON TDS TILL M.N. |  | -107
WellA | 2019-09-04 | 135 | 26 | 9 | CONT. D/O CMT TO 107M, POOH TO SURF., CHANGE BIT, RIH W/ 24" R.BIT#2 NEW TO 107 M, CONT. DRLG FORM. F/ 107 TO 135 M W/ NL-NG TILL M.N. |  | -135
WellA | 2019-09-05 | 161 | 26 | 10 | CLEAN THE WELL, POOH FOR P/U S.STAB F/ 135 TO SURF., RUN BACK TO HOLE W/2 NO. 24" S.STAB @ 10M, 20M TO 132 M, TAKE WEIGHT, W&R TO 135 M, CONT. DRLG FORM. F/ 135 TO 161 M W/ NL-NG TILL M.N | Start Drilling 26" Hole Section | -161
WellA | 2019-09-06 | 210 | 26 | 11 | CONT. DRLG FORM. W/2 NO. 24" S.STAB @ 10M, 20M F/ 161 TO 200 M W/ NL-NG, PUMP PILL & CLEAN THE WELL, DIS. BENTONITE MUD ( IN HOLE) W/ S.SATURATED MUD, CONT. DRLG FORM. F/ 200 TO 210 M W/ NL-NG TILL M.N |  | -210
WellA | 2019-09-07 | 282 | 26 | 12 | CONT. DRLG FORM. W/2 NO. 24" S.STAB @ 10M, 20M F/ 210 TO 282 M W/ VIBRATION & NL-NG WHILE INC. MW F/ 73 TO 75 PCF & PUMP HI-VIS PILL PERIODICALLY TILL M.N |  | -282
WellA | 2019-09-08 | 296 | 26 | 13 | CONT. DRLG FORM. W/2 NO. 24" S.STAB @ 10M, 20M F/ 282 TO 296 M W/ VIBRATION & NL-NG, RUN TOTCO @ 287 M, INC. 1.25 DEG. POOH TO SURF. CHANGE BIT & BHA. RIH W/ 24" PDC BIT#3 USED & 2 NO. 24" S.STAB @ 20M, 30M TO 136 M TILL M.N |  | -296
WellA | 2019-09-09 | 350 | 26 | 14 | CONT. RIH W/ 24" PDC BIT#3 USED & 2 NO. 24" S.STAB @ 20M, 30M TO 296 M, CONT DRLG FORM. F/ 296 TO 350 M W/ NL-NG WHILE PUMP HI-VIS PILL PERIODICALLY TILL M.N |  | -350
WellA | 2019-09-10 | 425 | 26 | 15 | CONT DRLG FORM. F/ 350 TO 425 M W/ NL-NG WHILE PUMP HI-VIS PILL PERIODICALLY & RUN TOTCO @ 398 M, INC.: 1 DEG. TILL M.N |  | -425
WellA | 2019-09-11 | 475 | 26 | 16 | CONT DRLG FORM. F/425 TO 473 M, NL-NG, STOP DRLG DUE TO NO CONTROL MW, POOH TO 260 M, RUN BACK TO BTM, CONT. DRLG FM TO 475 M, STOP DRLG DUE TO FAILURE TDS, WORK ON TDS, NL-NG TILL MN. |  | -475
WellA | 2019-09-12 | 529 | 26 | 17 | WORK ON TDS, RESUME DRLG FM F/475 TO 524 M WHILE WORK ON MW, PUMP HI-VIS PILL & CLEAN HOLE, RUN TOTCO, INC: 1 DEG, CONT. DRLG TO 529 M, OBS DEC. SPP 100 PSI, STOP DRLG, CHECK SURF. EQUIP TILL MN. |  | -529
WellA | 2019-09-13 | 529 | 26 | 18 | DROP PRESS 100 PSI, STOP DRLG & CHECK SURF. EQUIP. OK, CHANGE SPR, POOH TO SURF FOR CHECK STRG, OBS TWIST OFF STRING STRG F/FIRST 24" S.STAB IN BOX @ 24.28M & LEFT IN HOLE, RIH W/12-3/4" O.SHUT ASSY. & CATCH TOP OF FISH @ 504.72M, POOH TO SURF. & L/D OVER SHUT & TWIST OFF 24" S.STAB TILL MN. | Observed Twist off string from Stabilizer | -529
WellA | 2019-09-14 | 551 | 26 | 19 | L/D FISHING BHA & PDC BIT, P/U & M/U 24" USED PDC BIT # 3 RR1 & NEW BHA JT BY JT FOLLOWED 5" DP TO 500 M, WASH DOWN TO 529 M, START DRLG FM F/529 TO 551M, NL-NG. |  | -551
WellA | 2019-09-15 | 603 | 26 | 20 | CONT. DRLG FM F/551 TO 603 M WHILE INC. MW F/80 TO 82 PCF, NL-NG. |  | -603
WellA | 2019-09-16 | 642 | 26 | 21 | CHANGE WASH PIPE, CONT. DRLG F/603 TO 608M, RUN TOTCO, INC: 2 DEG, CONT. DRLG FM TO 642M, NL-NG, STOP DRLG, DUE TO CHANGE BHA, PUMP & CIRC. OUT 30 BBL HI-VIS PILL, DROP TOTCO, POOH TO 345M, NL-NG. |  | -642
WellA | 2019-09-17 | 667 | 26 | 22 | DUE TO CHANGE BHA POOH F/345 TO SURF. NL-NG, OBS WELL ON BHA STATIC, L/D 24" PDC BIT # 3 RR1 & 24" S.STAB. P/U & M/U 24" USED PDC BIT # 4 & DRLG BHA # 8 FOLLOWED 5" DP TO 642M, SHORT CIRC. RESUME DRLG FM TO 667M, NL-NG. |  | -667
WellA | 2019-09-18 | 714 | 26 | 23 | CONT. DRLG FM F/667 TO 705M WHILE INC MW F/82 TO 83 PCF, RUN TOTCO SURVEY @ 700M, INC:2 DEG, CONT. DRLG FM TO 714M, NL-NG TILL MN. |  | -714
WellA | 2019-09-19 | 746 | 26 | 24 | CONT. DRLG FM F/714 TO 726 M, WORK ON MUD PUMP 1&3, CONT DRLG TO 746 M, OBS DEC. PRESS, POOH F/ 746 TO 287 M WHILE CHECK THE STRG, OBS WASH OUT 1 JT 5" D.P (SLIPS AREA), CONT POOH TO 122 M WHILE L/D 15 JTS 5" H.W.D.P, OBS WASH OUT 11 JTS 5" H.W.D.P FROM CONNECTION CIRC C.W.H W/ NL-NG TILL M.N. |  | -746
WellA | 2019-09-20 | 756 | 26 | 25 | CONT. POOH TO SURF., L/D 24" PDC BIT & 2NO. 24" S.STAB & VISUALLY CHECK. ALL CONN., RIH W/24"USED PDC BIT & SAME BHA (P/U 5 STD 5" HWDP JT BY JT) TO 746M, (WORK ON TDS @ 30M), RESUME DRLG F/746 TO 756M, RUN TOTCO SURVEY, RESULT INC.: 1.25 DEG, WORK ON MUD PUMP # 2 WHILE CIRC. & MOVMENT STRG, NL-NG TILL MN. |  | -756
WellA | 2019-09-21 | 798 | 26 | 26 | CONT. WORK ON MUD PUMP# 2 & 3 @ 756M, RESUME DRLG TO 769M, WORK ON PUMP AGAIN, CONT. DRLG TO 785M, WORK ON TDS & PUMP, CONT. DRLG TO 798M, INC. MW F/84 TO 85 PCF AS PROGRAM, POOH TO 720M, WORK ON TDS SYS., RIH TO 798 M NL-NG TILL MN. |  | -798
WellA | 2019-09-22 | 848 | 26 | 27 | CONT. DRLG F/798 TO 806M, CIRC., GET SURVEY @ 800M, RESULT INC: 2DEG, CONT. DRLG F/806 TO 848M WHILE INC. MW F/85 TO 86 PCF AS PROGRAM, NL-NG. |  | -848
WellA | 2019-09-23 | 866 | 26 | 28 | CONT. DRLG FM F/848 TO 852M, GET SURVEY @ 850M, RESULT INC: 2DEG, CONT. DRLG TO 862M, STOP DRLG, CBU, WORK ON TDS, CONT. DRLG TO 866M, OBS DEC. PRESS 80 PSI, STOP DRLG, CHECK SURF. EQUIP. "OK", INC 1-2 STROKE, POOH WHILE CHECK STRG, OBS 5" DP CONNECTION & 2 JT @ CONNECTION HWDP IS WASHOUT TILL M.N. |  | -866
WellA | 2019-09-24 | 873 | 26 | 29 | CONT. POOH F/230 TO SURF. WHILE CHECK BHA, OBS 6 JT HWDP IS WASHOUT. P/U & M/U SAME 24" PDC BIT # 4 RR2 & BHA 10 FOLLOWED BY 5" DP TO 866M, RESUME DRLG F/866 TO 873M, NL-NG. |  | -873
WellA | 2019-09-25 | 916 | 26 | 30 | CONT DRLG F/873 TO 890 M WHILE INC. MW F/87 TO 88 PCF AS PROGRAM, NL-NG. WORK ON MUD PUMP 1&2. CONT DRLG F/890 TO 916 M, WAIT ON NIDC OPERATION DEPARTMENT DUE TO OBS DECREASE 40 PSI PRESS, CHECK SURF EQUIPMENT, OK & CHECK S.P.R, POOH F/ 916 TO 400 M WHILE CHECK STRG JT BY JT TILL M.N. |  | -916
WellA | 2019-09-26 | 932 | 26 | 31 | WHILE WAITING FOR NIDC OPERATION POOH F/ 400 TO SURF., L/D 5 JTs WASH OUT HWDPs. RIH W/ SAME PDC BIT & BHA #11 TO 916M (BTM). CONT. DRLG FORM. F/ 916 TO 932M. DUE TO GENERATOR FAILURE POOH F/ 932 TO 105 M (30 " CSG SHOE) TILL M.N. |  | -932
WellA | 2019-09-27 | 932 | 26 | 32 | WAITING FOR NIDC OPERATION DEPARTMENT DUE TO FAILURE GENERATOR #1 WHILE SLOW CIRC. MUD W/ NL-NG & WORK ON GENERATOR TILL M.N. |  | -932
WellA | 2019-09-28 | 973 | 26 | 33 | WAITING FOR NIDC OPERATION DEPARTMENT DUE TO FAILURE OF GENERATOR #1 WHILE RIH F/ 105 (30" SHOE) TO 932 M (BTM), CONT DRLG FORM. F/ 932 TO 973 M W/ NL-NG WHILE PUMPING PILL PERIODICALLY & RUN TOTCO @ 950 M, INC.: 1.5 DEG. TILL M.N. |  | -973
WellA | 2019-09-29 | 998 | 26 | 34 | CONT DRLG FORM. F/ 973 TO 989M, OBS. DEC SPP, POOH TO 121 M & L/D WASH OUT D.P. RIH TO 989M, CONT DRLG FORM. F/ 989 TO 998 M ( CSG POINT). INC. MW F/ 88 TO 90 PCF IN PROGRESS TILL M.N. | Finish Drilling 26" Hole | -998
WellA | 2019-09-30 | 998 | 26 | 35 | INC. MW F/ 88 TO 90 PCF, RUN TOTCO @ 998 M, INC.: 1.5 DEG, SPOT 300 BBL HI-VIS PILL, POOH TO SURF. R/U CSG EQUIP., RUN 18-5/8" CSG TO 380 M TILL M.N. |  | -998
WellA | 2019-10-01 | 998 | 26 | 36 | CONT RUN 18-5/8" CSG F/ 380 TO 998 M, TAG BTM WHILE FILL UP STRING EVERY 8 JT S W/ NL-NG & USE CENTERALIZER AS PROGRAM TILL M.N. | Run 20" CSG | -998
WellA | 2019-10-02 | 998 | 26 | 37 | R/D CSG RUNNING EQUIP., P/U & M/U 5" STINGER & RIH TO 974M ( F.C DEPTH), STING IN & SHORT CIRC. MUD, PERFORM 18-5/8" CSG CMT JOB AS PROGRAM, W.OC WHILE POOH INSIDE STRING F/ 974 TO 520 M TILL M.N. | Perform CMT Job | -998
WellA | 2019-10-03 | 998 | 26 | 38 | W.O.C WHILE CONT POOH 5" DP STRING F/ 520 TO SURF., N/D 30" BOP STACK, DRESS & BEVEL 18-5/8" CSG NECK, INSTALL & LEVEL 20-3/4" C.H.H ( 3K, MSP DRILLEX, WELD TYPE), WELD 20 3/4" C.H.H ON 18 5/8" CSG NECK & WAIT TILL WELDED AREA BE COLD TILL M.N. |  | -998
WellA | 2019-10-04 | 998 | 26 | 39 | TEST 20 3/4" C.H.H W/400 PSI & TWO 2 1/6", 5K SIDE VAVES W/ 3000 PSI, "OK" , N/U 20 3/4"-3K BOP STACK & RECTIFY LEAKAGES, PERFORM 20-3/4" BOP STACK TEST AS NIDC POLICY TILL M.N. |  | -998
WellA | 2019-10-05 | 998 | 26 | 40 | WHILE WAITING FOR NIDC DRILLING FLUID MGT, RIH W/ B.BIT #5 NEW (TSK, 437, 3*20+ C.J 18) TO 955 M, TAKE WEIGHT, D/O SOFT TO HARD CMT F/ 955 TO 974 M (F.C DEPTH), PERFORM 18-5/8" CSG INTEGRITY TEST, "OK", CONT. D/O MED TO HARD CMT TO 984 M TILL M.N. |  | -998
WellA | 2019-10-06 | 1006 | 17.5 | 41 | CONT. D/O MED TO HARD CMT TO 998 M, COMMENCE DRLG 17" HOLE SECTION F/ 998 TO 1003 M, PERFORM 17" HOLE FIT, DIS. 90 PCF HOLE MUD W/ 100 PCF MUD, CONT. DRLG FORM. F/ 1003 TO 1006 M TILL M.N. | Start Drilling | -1006
WellA | 2019-10-07 | 1023 | 17.5 | 42 | CONT DRLG FORM. W/ 17" B.BIT # 5 NEW (TSK, 437, 3*20 + C.J 18) F/ 1006 TO 1023 M, CIRC BTM S UP, POOH STRG FOR JUNK SUB TRIP F/ 1023 TO 460 M WHILE CIRC. C.W.H W/ NL-NG TILL M.N. |  | -1023
WellA | 2019-10-08 | 1023 | 17.5 | 43 | POOH STRG F/ 460 M TO SURF., RIH W/ SAME BIT & 17" JUNK SUB TO 1023 M (BTM), WORK ON JUNK SUB SEVERAL TIMES, POOH TO SURF., L/D JUNK SUB ( RECOVER 0.1 LB JUNK), RIH W/ PDC BIT#6 NEW (BESTE, SN: 234352, 4*13+ 4* 14) & BHA#13 TO 93 M TILL M.N. |  | -1023
WellA | 2019-10-09 | 1023 | 17.5 | 44 | CONT RIH W/ PDC BIT#6 NEW (BESTE, SN: 234352, 4*13+ 4* 14) & BHA#13 TO 1023M, CIRC MUD& INC MUD WT T0 108 PCF TILL M.N. |  | -1023
WellA | 2019-10-10 | 1023 | 17.5 | 45 | CONT WAIT ON REC. MUD MATERIAL WHILE CIRC MUD @ 991 MT (18-5/8" CSG SHOE @ 997.5M), W/NL-NG . |  | -1023
WellA | 2019-10-11 | 1078 | 17.5 | 46 | CONT WAIT ON REC. MUD MATERIAL WHILE CIRC MUD @ 991 MT (18-5/8" CSG SHOE @ 997.5M), W/NL-NG, REC BARITE (TOTALLY STOCK:129 TN), START DRLG FM F/1023 TO 1078 M W/0-24BPH LOSS TILL MN. |  | -1078
WellA | 2019-10-12 | 1149 | 17.5 | 47 | CONT. DRLG FM F/1078 TO 1115M WHILE DEC. MW F/108 TO 106PCF, 6-12BPH LOSS, RUN TOTCO SURVEY, RESULT INC: 1DEG, CONT. DRLG F/1115 TO 1149M WHILE DEC. MW F/106 TO 105 PCF, 2-4BPH LOSS. |  | -1149
WellA | 2019-10-13 | 1206 | 17.5 | 48 | CONT. DRLG FM F/1149 TO 1188M, WORK ON MUD PUMP # 2, CONT. DRLG F/1188 TO 1206M, NL-NG. |  | -1206
WellA | 2019-10-14 | 1232 | 17.5 | 49 | CONT. DRLG 17" HOLE SECTION F/1206 TO 1232M, WHILE WORK ON MUD PUMP # 1-2-3 & CHANGE WASH PIPE, NL-NG, RUN TOTCO SURVEY @ 1200M, INC: 3/4 DEG TILL M.N |  | -1232
WellA | 2019-10-15 | 1289 | 17.5 | 50 | CONT. DRLG 17" HOLE SECTION F/1232 TO 1254M, CHANGE WASH PIPE, CONT. DRLG TO 1289M, NL-NG TILL MN. |  | -1289
WellA | 2019-10-16 | 1289 | 17.5 | 51 | DUE TO FAILURE & SHUT DOWN TDS, C.BU WHILE MOVEMENT STRG, L/D 1JT 5" DP, TRY TO L/D SECOND JOINT STUCK STRG @ 1276M, WORK ON STUCK STRG W/PUMPING 4 STEP SALT WTR @ APPLY TRQ & WEIGHT DOWNWARD, FREE STRG, CIRC. TILL BALANCE MW TO 105PCF, POOH FOR CHECK COND. F/1276 TO 1220M W/B.REAM TILL MN. |  | -1289
WellA | 2019-10-17 | 1295 | 17.5 | 52 | CONT. CHECK COND. F/1220 TO 997M, B.REAM SOME POINT(1220M-1046M), WORK ON TDS, OBS WELL "STATIC", DUE TO CHECK STRG POOH F/997 TO 122M (BHA), OK", OBS WELL STATIC, RUN BACK TO 1280M, W & R TO 1289M (BTM), RESUME DRLG TO 1292M, CHANGE WASH PIPE, CONT. DRLG TO 1295M, WHILE INC. MW F/105 TO 106M, NL-NG TILL M.N |  | -1295
WellA | 2019-10-18 | 1321 | 17.5 | 53 | CONT. DRLG FM F/1295 TO 1321M, NL-NG. WORK ON MUD PUMP SEVERAL TIMES & WHASH PIPE WHILE CIRC. TILL M.N |  | -1321
WellA | 2019-10-19 | 1358 | 17.5 | 54 | CONT. DRLG 17" HOLE SECTION F/1321 TO 1358M, NL-NG, WORK ON MUD PUMP # 1,2,3 SEVERAL TIMEs. DUE TO NOT EXISTENCE EQUIP. FOR MUD PUMP, POOH TO 997M( 18-5/8" CSG SHOE) WHILE F/U WELL CONTINUOUSLY, NL-NG. |  | -1358
WellA | 2019-10-20 | 1358 | 17.5 | 55 | WHILE WAIT ON REC. MUD PUMPS EQUIP. CONT. POOH F/997.5M TO SURF. OBS WELL ON SHOE & BHA "STATIC", L/D 17" PDC BIT, PERFORM BOP TEST AS NIOC POLICY, RIH W/NEW 17" PDC BIT & SAME BHA # 14 TO 500M, NL-NG TILL MN. |  | -1358
WellA | 2019-10-21 | 1358 | 17.5 | 56 | WHILE WAIT ON REC. MUD PUMPS EQUIP. CONT. RIH F/500 TO 997.5M, SLOW CIRC. MUD & MOVEMENT STRG, NL-NG TILL M.N |  | -1358
WellA | 2019-10-22 | 1358 | 17.5 | 57 | WHILE WAIT ON REC. MUD PUMPS EQUIP. CONT. CIRC. MUD & MOVEMENT STRG @997.5M(18-5/8" CSG SHOE), NL-NG TILL M.N |  | -1358
WellA | 2019-10-23 | 1378 | 17.5 | 58 | WHILE WAIT ON REC. MUD PUMPS EQUIP. CONT. CIRC. MUD @997.5M, RECEIVE EQUIP. REPAIR & CHECK MUD PUMPS, OK. RIH F/ 997.5 TO 1358 M ( BTM ), CONT. DRLG 17" HOLE SECTION F/ 1358 TO 1378 M W/ NL-NG TILL M.N |  | -1378
WellA | 2019-10-24 | 1417 | 17.5 | 59 | C.B.U & RUN TOTCO SURVEY@ 1367 M, RESULT INC.: 0.5 DEG, CONT. DRLG 17" HOLE SECTION F/ 1378 TO 1417 M W/ NL-NG WHILE WORK ON TDS WASH PIPE & MUD PUMP TILL M.N |  | -1417
WellA | 2019-10-25 | 1495 | 17.5 | 60 | CONT DRLG FORM F/ 1417 TO 1495 M W/ NL-NG WHILE INC. MW F/ 106 TO 108 PCF DUE TO TIGHT HOLE & OBS. PIPE STUCK @ 1413 M TILL M.N |  | -1495
WellA | 2019-10-26 | 1539 | 17.5 | 61 | CONT DRLG FORM F/ 1495 TO 1539 M W/ NL-NG TILL M.N |  | -1539
WellA | 2019-10-27 | 1594 | 17.5 | 62 | CONT DRLG FORM F/ 1539 TO 1594 M W/ NL-NG WHILE WASH & BACKREAM EACH STD TILL M.N |  | -1594
WellA | 2019-10-28 | 1629 | 17.5 | 63 | CONT DRLG FORM F/ 1594 TO 1629 M W/ NL-NG WHILE WASH & BACKREAM EACH STD, STUCK STRG @ 1627M, WORK ON STUCK TILL FREE STRG, W&R LAST STD WHILE INC MW F/ 108 TO 109 PCF IN PROGRESS TILL M.N |  | -1629
WellA | 2019-10-29 | 1632 | 17.5 | 64 | BALANCE MW ON 109 PCF @ 1629 M, POOH AS CONDITION TRIP F/ 1629 TO 997.5 (18-5/8" SHOE), RUN BACK TO 1629 M (BTM) WHILE INC MW F/ 109 TO 111 PCF, CONT. DRLG FORM F/ 1629 TO 1632 M W/ NL-NG TILL M.N |  | -1632
WellA | 2019-10-30 | 1668 | 17.5 | 65 | CONT. DRLG FORM F/ 1632 TO 1668 M W/ NL-NG, CIRC. BTM S UP, DROP TOTCO SURVEY @ 1667 M, POOH FOR CHANGE BHA F/ 1668 TO 1300 M TILL M.N |  | -1668
WellA | 2019-10-31 | 1668 | 17.5 | 66 | CONT. POOH FOR CHANGE BHA F/ 1300 TO SURF WHILE L/D ALL D.Cs & HWDPs, RECOVER TOTCO: INC 0.25 DEG @1667 M. RIH W/ NEW PDC BIT & BHA # 15 TO 1190 M TILL M.N |  | -1668
WellA | 2019-11-01 | 1685 | 17.5 | 67 | CONT. RIH W/ NEW PDC BIT & BHA # 15 F/ 1190 TO 1668 M (BTM), CONT. DRLG 17" HOLE SECTION F/ 1668 TO 1685 M W/ NL-NG TILL M.N |  | -1685
WellA | 2019-11-02 | 1709 | 17.5 | 68 | CONT. DRLG 17" HOLE SECTION F/ 1685 TO 1709 M W/ NL-NG TILL M.N |  | -1709
WellA | 2019-11-03 | 1744 | 17.5 | 69 | CONT. DRLG 17" HOLE SECTION F/ 1709 TO 1744 M W/ NL-NG WHILE BACKREAM EACH STD TILL M.N |  | -1744
WellA | 2019-11-04 | 1793 | 17.5 | 70 | CONT. DRLG 17" HOLE SECTION F/ 1744 TO 1793 M W/ 0-6 BPH LOSS WHILE BACKREAM EACH STD TILL M.N |  | -1793
WellA | 2019-11-05 | 1817 | 17.5 | 71 | CONT. DRLG 17" HOLE SECTION F/ 1793 TO 1817 M W/ 0-2 BPH LOSS WHILE BACKREAM EACH STD TILL M.N |  | -1817
WellA | 2019-11-06 | 1832 | 17.5 | 72 | CONT. DRLG 17" HOLE SECTION F/1817 TO 1832M, DUE TO FAILURE MUD PUMPS & SHORTAGE MUD PUMP EQUIP. PUMP OUT F/1832(BTM) TO 1685M, CONT. POOH TO 997.5M(18-5/8" CSG SHOE) W/GOOD HOLE COND., OBS WELL STATIC, DUE TO CHANGE PDC BIT POOH F/997.5 TO 286M, OBS WELL ON BHA "STATIC", TILL MN. |  | -1832
WellA | 2019-11-07 | 1832 | 17.5 | 73 | CONT. POOH F/286 TO SURF., L/D 17" S.STAB & PDC BIT. PERFORM BOP TEST AS NIOC POLICY. P/U & M/U 17" NEW B.BIT & BHA # 15 TO 316M, WORK ON TDS, CONT. RIH F/316 TO 1752M, W/GOOD HOLE COND., W & R F/1752 TO 1832M, CIRC. MUD BY WELL SITE GEOLOGIST, NL-NG TILL M.N |  | -1832
WellA | 2019-11-08 | 1849 | 17.5 | 74 | RESUME DRLG 17" HOLE SECTION F/1832 TO 1849M, WHILE WORK ON MUD PUMP & TDS & DRAWWORKS, 0-2 BPH LOSS. |  | -1849
WellA | 2019-11-09 | 1864.7 | 17.5 | 75 | CONT. DRLG FM F/1849 TO 1864.70M, 0-2 BPH LOSS. |  | -1864.7
WellA | 2019-11-10 | 1872.4 | 17.5 | 76 | CONT. DRLG FM F/1864.70 TO 1872.4M, 0-2BPH LOSS TILL M.N |  | -1872.4
WellA | 2019-11-11 | 1877 | 17.5 | 77 | CONT. DRLG FM F/1872.4 TO 1877M, 0-2BPH LOSS, CONFIRM 13-5/8" CSG POINT @ THIS POINT, CIRC. MUD WHILE INC. MW F/111 TO 113 PCF TILL M.N |  | -1877
WellA | 2019-11-12 | 1877 | 17.5 | 78 | CONT. CIRC. MUD TILL UNIFORM MW TO 113PCF, POOH AS COND. TRIP F/1877 TO 1700M W/B.REAM, REAM & B.REAM THIS INTERVAL & CHECK COND. "OK", CONT. POOH TO 997.5M (18-5/8" CSG SHOE) W/GOOD COND., OBS WELL"STATIC", BOP DRILL, RUN BACK TO 1747M, TOOK WEIGHT, W & R TO 1770M, RIH TO 1857M, TOOK WEIGHT, W & R TO 1877M (13-5/8" CSG POINT), C. B.U TILL CLEAN SHAKER. |  | -1877
WellA | 2019-11-13 | 1877 | 17.5 | 79 | START POOH F/1887 TO 997.5M, W/GOOD COND. OBS WELL @ SHOE "STATIC", CONT. POOH F/997.5 TO SURF., OBS WELL ON BHA "STATIC", L/D 17" B.BIT, R/U LOGGING TOOLS & RIH RUN # 1 W/SONC-CALIPER-CDR-GR TO 1322M, DROP TENSION, POOH TO SURF., L/D CALIPER, SONIC TOOLS, RIH RUN # 2 W/CDR-GR TO 1877M, LOG UP TO SURF., L/D LOGGING EQUIP., INSTAL W.BUSHING, RIH W/17" USED B.BIT # 9 RR1 & S.STAB @ 20M TO 60M, 0-1 BPH LOSS TILL M.N |  | -1877
WellA | 2019-11-14 | 1877 | 17.5 | 80 | CONT. RIH W/17" USED B.BIT & 17" S.STAB @ 20M TO 350M, TWISTING DRLG LINE, WORK ON IT, CONT. RIH TO 950M, SLIP & CUT DRLG LINE, CONT. RIH AS COND. TRIP TO 1060M, TOOK WEIGHT, W & R TO 1240M, 1-2BPH LOSS TILL M.N |  | -1877
WellA | 2019-11-15 | 1877 | 17.5 | 81 | CONT. W & R F/1240 TO 1685M WHILE INC. MW F/113 TO 115PCF @ 2 STAGE, OBS WELL 0-2 BPH LOSS TILL M.N |  | -1877
WellA | 2019-11-16 | 1877 | 17.5 | 82 | CONT. W & R F/1685 TO 1877M WHILE INC. MW F/115 TO 117PCF STEP BY STEP, 0-2 BPH LOSS TILL M.N |  | -1877
WellA | 2019-11-17 | 1877 | 17.5 | 83 | CONT. CIRC. MUD TILL BALANCE MW TO 117PCF, DUE TO CHECK COND. POOH F/1877 TO 1665M, B.REAM TO 1657M, CONT. POOH TO 1470M, B.REAM TO 1400M, CONT. POOH F/1400 TO 997.5M(SHOE), PUMP 50 BBL SALT WTR FOR CLEAN BIT & STAB, RIH TO CHECK COND. F/997.5 TO 1483M, TOOK WEIGHT, W & R TO 1570M WHILE INC. MW TO 119 PCF, 0-2 BPH LOSS. |  | -1877
WellA | 2019-11-18 | 1877 | 17.5 | 84 | CONT. W & R F/1570 TO 1877M(BTM) WHILE INC. MW F/117 TO 1179PCF, C.B.U, POOH AS COND. TRIP, OBS WELL @ SHOE,STATIC, RIH AS COND. TRIP TO 1877M W/GOOD COND., 0-2 BPH LOSS TILL M.N |  | -1877
WellA | 2019-11-19 | 1877 | 17.5 | 85 | CIRC. MUD @ 1877M(BTM) TILL CLEAN HOLE, SPOT 300BBL HI-VIS PILL, START POOH FOR RUN CSG F/BTM TO 18-5/8" CSG SHOE W/GOOD COND., OBS WELL "STATIC", CONT. POOH TO SURF., L/D 17" B.BIT. REMOVE W.BUSHING, CHANGE RAMS, R/U CSG RUNNING EQUIP. & RUN 13-5/8" CSG SHOE + 4 JT 13-5/8" CSG + 13-5/8" COLLAR + 1JT 13-5/8" CSG TO 59.262M, CIRC. & CHECK SHOE & COLLAR "OK". |  | -1877
WellA | 2019-11-20 | 1877 | 17.5 | 86 | CONT. RIH CSG (TOTALLY 84 JTs 13-5/8"(88.2#) & 76 JTs 13-3/8"(72#)) F/ 59 TO 1877 M (BTM) WHILE FILL UP STRING EACH JTs & M/UP CENTRALIZER AS PROGRAM TILL M.N. |  | -1877
WellA | 2019-11-21 | 1877 | 17.5 | 87 | WAITING FOR NIDC CEMENT DEPT. WHILE SLOW CIRC MUD THROUGH CSG STRING W/ 0-1 BPH LOSS & CUT MW F/ 119 TO 117 PCF AS PROGRAM ( STEP BY STEP) TILL M.N. |  | -1877
WellA | 2019-11-22 | 1877 | 17.5 | 88 | CONT PREPARE CMT SOLUTION, PERFORM CSG CMT JOB, INSTALL CSG SLIPS & TEST IT. WORK ON N/D BOP STACK IN PROGRESS TILL M.N. |  | -1877
WellA | 2019-11-23 | 1877 | 17.5 | 89 | N/D 20-3/4" BOP STACK, DRESS & BEVEL 13-3/8" CSG NECK, INSTALL 20-3/4", 3K * 13-5/8", 5K DSA + 13 5/8" * 13 5/8", 5K C.H.S, N/UP 13 5/8"-10K BOP STACK IN PROGRESS TILL M.N. |  | -1877
WellA | 2019-11-24 | 1877 | 17.5 | 90 | N/UP 13 5/8"-10K BOP STACK & WORK ON REMOVE LEAKAGES TILL M.N. |  | -1877
WellA | 2019-11-25 | 1877 | 17.5 | 91 | WORK ON REMOVE 13 5/8"-10K BOP STACK LEAKAGES, TEST BOP STACK AS NIDC POLICY. L/D 6 JTs 9-3/4" DC. P/U & M/U 12 1/4" R.BIT#10 NEW TILL M.N. |  | -1877
WellA | 2019-11-26 | 1877 | 17.5 | 92 | RIH W/ 12 1/4" R.BIT#10 NEW & 6 JTS 8-1/2" DC NEW (JT BY JT) FOLLOW BY 99 JTS 5" UBD DP (JT BY JT) TO 1000 M, POOH TO SURF., INSTALL ROTATING HEAD IN PROGRESS TILL M.N. |  | -1877
WellA | 2019-11-27 | 1877 | 17.5 | 93 | INSTALL ROTATING HEAD & TEST W/ 600 PSI "OK", RIH W/ 12 1/4" R.BIT & BHA #17 TO 870M, MAKE 27 STD 5" UBD DP, L/D 90 JTS 5" DP. RIH W/ 12 1/4" R.BIT & BHA #17 FOLLOW BY 5" DP F/ 269 TO 650 M TILL M.N. |  | -1877
WellA | 2019-11-28 | 1877 | 17.5 | 94 | CONT. RIH W/ 12 1/4" R.BIT & BHA #17 FOLLOW BY 5" DP F/ 650 TO 1790 M, TAG TOP OF CMT @ 1790 M (F.C @ 1829 M). D/OUT CMT F/ 1790 TO 1828 M, CIRC. BTM S UP, SLOW CIRC. MUD TILL M.N. |  | -1877
WellA | 2019-11-29 | 1877 | 17.5 | 95 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-11-30 | 1877 | 17.5 | 96 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-01 | 1877 | 17.5 | 97 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-02 | 1877 | 17.5 | 98 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-03 | 1877 | 17.5 | 99 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-04 | 1877 | 17.5 | 100 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-05 | 1877 | 17.5 | 101 | CLIENT (NISOC) WAITING DUE TO CHANGE 12 1/4" HOLE SECTION PROGRAM TILL M.N. |  | -1877
WellA | 2019-12-06 | 1877 | 17.5 | 102 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM& CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG TILL M.N |  | -1877
WellA | 2019-12-07 | 1877 | 17.5 | 103 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM& CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH |  | -1877
WellA | 2019-12-08 | 1877 | 17.5 | 104 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG. |  | -1877
WellA | 2019-12-09 | 1877 | 17.5 | 105 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG. |  | -1877
WellA | 2019-12-10 | 1877 | 17.5 | 106 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG. |  | -1877
WellA | 2019-12-11 | 1877 | 17.5 | 107 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-12 | 1877 | 17.5 | 108 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-13 | 1877 | 17.5 | 109 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-14 | 1877 | 17.5 | 110 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-15 | 1877 | 17.5 | 111 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-16 | 1877 | 17.5 | 112 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-17 | 1877 | 17.5 | 113 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-18 | 1877 | 17.5 | 114 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-19 | 1877 | 17.5 | 115 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-20 | 1877 | 17.5 | 116 | CLIENT (NISOC) WAITING DUE TO CHANGE DRLG PROGRAM & CONFIRM NEW PROGRAM F/VERTICAL TO DIRECTIONAL BY CLIENT , SLOW CIRC MUD THROUGH STRG @ 1810M, TILL M.N |  | -1877
WellA | 2019-12-21 | 1877 | 17.5 | 117 | CLIENT (NISOC) WAITING TILL 17:00 O CLOCK, RIH F/ 1810 TO 1828 M (BTM), D/OUT HARD CMT & BTM PLUG & FLOAT COLLAR ( F.C @ 1829 M) F/ 1828 TO 1832 M, PERFORM CIT W/ 1500 PSI, OK TILL M.N |  | -1877
WellA | 2019-12-22 | 1878 | 12.25 | 118 | CONT D/OUT CMT & F.SHOE TO 1876.5 M(SHOE DEPTH), DRLG 12-1/4" HOLE SECTION F/ 1876.5 TO 1878 M, POOH TO 1000 M, DISPLACE HOLE MUD W/ FRESH MUD (63 PCF), RIH F/ 1000 TO 1878 M (BTM) TILL M.N |  | -1878
WellA | 2019-12-23 | 1885 | 12.25 | 119 | DISPLACE HOLE MUD W/ FRESH MUD (63 PCF), RESUME DRLG 12-1/4" HOLE SECTION F/ 1878 TO 1885 M, POOH F/1885 TO SURF., RIH W/ 12 1/4" R.BIT#10RR1 + 12-1/4" JUNK SUB TO 150M TILL M.N |  | -1885
WellA | 2019-12-24 | 1885 | 12.25 | 120 | RIH W/ 12 1/4" R.BIT#10RR1 + 12-1/4" JUNK SUB TO 1885 M(BTM), WORK ON JUNK SUB, POOH TO SURF., L/D 15 JTS HWDP & 6 JTS DC, RECOVER 0.5 LB JUNK, TEST BOP STACK AS NIDC POLICY TILL M.N |  | -1885
WellA | 2019-12-25 | 1888 | 12.25 | 121 | RIH W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M TO 1885 M, CONT DRLG 12-1/4" HOLE SECTION F/ 1885 TO 1888 M W/ 6-8 BPH LOSS TILL M.N. |  | -1888
WellA | 2019-12-26 | 1928 | 12.25 | 122 | CONT DRLG W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M F/ 1888 TO 1928 M W/ 10-14 BPH LOSS WHILE BY-PASS SHALE SHAKER & PUMP HI-VIS LCM PILL PERIODICALLY TILL M.N. |  | -1928
WellA | 2019-12-27 | 1957 | 12.25 | 123 | CONT DRLG W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M F/ 1928 TO 1957 M W/ 8-10 BPH LOSS WHILE BY-PASS SHALE SHAKER & PUMP HI-VIS LCM PILL PERIODICALLY TILL M.N. |  | -1957
WellA | 2019-12-28 | 2030 | 12.25 | 124 | CONT DRLG W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M F/ 1957 TO 2030 M W/ 8-10 BPH LOSS WHILE BY-PASS SHALE SHAKER & PUMP HI-VIS LCM PILL PERIODICALLY TILL M.N. |  | -2030
WellA | 2019-12-29 | 2072 | 12.25 | 125 | CONT DRLG W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M F/ 2030 TO 2072 M W/ 8-10 BPH LOSS WHILE BY-PASS SHALE SHAKER & PUMP HI-VIS LCM PILL PERIODICALLY TILL M.N. |  | -2072
WellA | 2019-12-30 | 2115 | 12.25 | 126 | CONT DRLG W/ 12 1/4" PDC BIT#11 NEW (K.D, 1363, 8*15) & 12-1/4" S.STAB @ 20M F/ 2072 TO 2115 M W/ 8-10 BPH LOSS WHILE BY-PASS SHALE SHAKER & PUMP HI-VIS LCM PILL PERIODICALLY TILL M.N. |  | -2115
WellA | 2019-12-31 | 2155 | 12.25 | 127 | CONT DRLG W/ 12 1/4" PDC BIT & 12-1/4" S.STAB @ 20M F/ 2115 TO 2155 M W/ 10-12 BPH LOSS, CIRC BTM S UP, SPOT 100 BBL HI-VIS LCM PILL, POOH FOR PERFORM BOP TEST F/ 2155 TO 1870 M WHILE CIRC C.W.H W/ 8-10 BPH LOSS TILL M.N. |  | -2155
WellA | 2020-01-01 | 2155 | 12.25 | 128 | CONT. POOH TO SURF., WHILE C.W.H W/8-10 BPH LOSS, OBS WELL @ SHOE & BHA, 8-10 BPH LOSS, L/D BIT, BOP TEST AS NIOC POLICY, BTM & SHEAR RAMS "NOT OK", P/U & M/U 8-3/8" C.CUT BIT FOLLOWED 5" DP TO 700M, 8-10 BPH LOSS. |  | -2155
WellA | 2020-01-02 | 2155 | 12.25 | 129 | RIH W/8-3/8" C.CUT BIT TO 1930M, CIRC. W/300 GPM, 16BPH LOSS, PUMP & SPOT 50 BBL LCM PILL, POOH TO 1820M, PUMP & SPOT 70BBL HI-VIS PILL, POOH TO 1670M, CIRC. & OBS 16-6BPH LOSS, PUMP 100BBL CMT 95PCF, DISPLACE W/82.5 BBL MUD, POOH 12 STD, FLUSH STRG, POOH TO 1100M, W.O.C WHILE C.W.H NL-NG. |  | -2155
WellA | 2020-01-03 | 2155 | 12.25 | 130 | WHILE WAIT ON WORK ON BOP LEAKAGE, W.O.C @ 1100M, RIH W/8-3/8" C.CUT BIT TO 1495M, TOOK WEIGHT, WASH DOWN TO 1497M, C.B.U, TEST CMT W/500PSI "OK", POOH F/1497 TO SURF. L/D BIT. P/U 12-1/4" R.BIT + 13-5/8" SCRAPER TO 160M, SCRAPE F/140 TO 160M SEVERAL TIMES TILL MN. |  | -2155
WellA | 2020-01-04 | 2155 | 12.25 | 131 | DUE TO WORK ON BOP LEAKAGE, SCRAPER TRIP TO 160M, SCRAPE F/140 TO 160M, POOH TO SURF., P/U 13-5/8" RTTS TOOLS (21 STD 5" DP TAIL) TO 154M., B.OFF 5" DP, POOH TO SURF. OBS B.OFF F/R.C VALVE, RIH TO 154M, CONNECTION TO RTTS STRING, UNSET IT, POOH TO SURF. & CHECK IT, RIH AGAIN TO 153.5M, SET RTTS PACKER & TEST IT, P.OFF 5" DP TO SURF. WORK ON CHANGE BONNET SEAL TILL MN. |  | -2155
WellA | 2020-01-05 | 2155 | 12.25 | 132 | WORK ON BOP STACK, TEST TOP, BTM, SHEAR RAMS W/4500PSI "OK", WORK ON SIDE OUTLET VALVES, CHECK & TEST THEM "OK", REMOVE PLUG TESTER, UNSET RTTS, RIH W/D/OUT BHA FOLLOWED 5" DP TO 1200M WHILE F/U STRG EACH 10STD, NL-NG. |  | -2155
WellA | 2020-01-06 | 2155 | 12.25 | 133 | CONT. RIH F/1200 TO 1475M, TOOK WEIGHT, D/OUT MED TO HARD CMT F/1475 TO 1689M, NL-NG, OBS SUDDENLY KICK, SOFT SHUT IN THE WELL, CIRC. W/CHOKE MANIFOLD & POORBOY DEGASER, C.B.U, OBS WELL STATIC, CONT. D/OUT F/1689 TO 1694M, 4BPH LOSS. |  | -2155
WellA | 2020-01-07 | 2155 | 12.25 | 134 | CONT. D/OUT CMT F/1692 TO 1724M, OBS KICK WELL, SHUT IN THE WELL, CIRC. TRUE CHOKE, OPEN WELL, PUMP DOWN TO 1876.5M, CIRC. TRUE CHOKE, PUMP DOWN TO 2155M, C.B.U TRUE CHOKE, PUMP 50BBL HI-VIS PILL, CIRC. OUT PILL, POOH TO SHOE, OBS WELL, 4BPH LOSS, INC. MW F/63 TO 64PCF, TILL M.N |  | -2155
WellA | 2020-01-08 | 2155 | 12.25 | 135 | CONT. POOH TO SURF., OBS WELL 2BPH LOSS, L/D 12-1/4" R.BIT, P/U 12-1/4" PDC BIT & S.STAB @ 20M, RIH TO 1876.5M, CIRC. WHILE DEC MW F/64 TO 63PCF., W & R F/1892 TO 1954M, 3-4BPH LOSS. |  | -2155
WellA | 2020-01-09 | 2197 | 12.25 | 136 | CONT. W & R F/1954 TO 2155M (BTM), RESUME DRLG FM F/2155 TO 2197M, 3-4BPH LOSS TILL M.N |  | -2197
WellA | 2020-01-10 | 2251 | 12.25 | 137 | CONT. DRLG FM F/2197M TO 2251M, WHILE PUMP LCM & HI-VIS PILL PERIODICALLY, 4-5BPH LOSS TILL M.N |  | -2251
WellA | 2020-01-11 | 2310 | 12.25 | 138 | CONT. DRLG FM F/2251M TO 2310M WHILE PUMP LCM & HI-VIS PILL PERIODICALLY, 3-4BPH LOSS, ADD 1% KCL TO MUD SYS, STUCK PIPE WHILE DRLG @ 2280 & 2302M, WORK ON STUCK & FREE STUCK @ 2 STAGE TILL M.N |  | -2310
WellA | 2020-01-12 | 2352 | 12.25 | 139 | CONT. DRLG FM F/2310 TO 2340M WHILE ADD KCL SYS TO 3%, PUMP LCM PHPA PILL EACH JOINT, 2-4BPH LOSS., WIPER TRIP W/B.REAM F/2340 TO 2200M, RIH TO 2331M W/GOOD COND., W & R TO 2340M, STUCK STRG @ 2338 M WORK ON & FREE STRG, CONT. DRLG TO 2352M, 2-4BPH LOSS. |  | -2352
WellA | 2020-01-13 | 2401 | 12.25 | 140 | CONT. DRLG FM F/2352 TO 2401M WHILE PUMP 20BBL LCM PHPA PILL EACH JOINT, 4-5BPH LOSS TILL M.N |  | -2401
WellA | 2020-01-14 | 2413 | 12.25 | 141 | CONT. DRLG F/2401 TO 2413M (9-5/8" CSG POINT), PUMP PILL & C.B.U TILL GET LAST SAMPLE BY WELL SITE GEOLOGIST & CLEAN SHAKER, POOH W/HARD B.REAM F/2413 TO 2154, 3-4BPH LOSS TILL M.N |  | -2413
WellA | 2020-01-15 | 2413 | 12.25 | 142 | POOH W/ HARD B.REAM F/ 2154 TO 1876.5 (13-5/8" CSG SHOE), SLIP & CUT 102 FT DRLG LINE, RUN BACK TO 2150 M W/ GOOD HOLE CONDITION TILL M.N |  | -2413
WellA | 2020-01-16 | 2413 | 12.25 | 143 | RIH TO 2413 M WHILE INC MW F/ 67 TO 70 PCF (TWO STEP), POOH F/ 2413 TO 1876.5 (13-5/8" CSG SHOE), RUN BACK TO 2413 M (BTM), CIRC MUD WHILE WORK ON MUD RHEOLOGY TILL M.N |  | -2413
WellA | 2020-01-17 | 2413 | 12.25 | 144 | CONT WORK ON MUD RHEOLOGY, POOH F/ 2413 TO 1876.5 (13-5/8" CSG SHOE) WHILE W&R SOME INTERVALS & INC MW F/ 70 TO 71 PCF, RUN BACK TO 2100 M WHILE W&R EACH STD F/ 1986 TO 2100 M TILL M.N |  | -2413
WellA | 2020-01-18 | 2413 | 12.25 | 145 | CONT RIH TO 2243 M WHILE INC MW TO 72 PCF, POOH TO CSG SHOE, RUN BACK TO 2413(BTM), CIRC BTM S UP, SPOT 350 BBL HI-VIS PILL. POOH FOR RUN 9-5/8" CSG F/ 2413 TO 300 M TILL M.N |  | -2413
WellA | 2020-01-19 | 2413 | 12.25 | 146 | CONT. POOH F/ 300 M TO SURF., CHANGE TOP RAMS, R/U CSG RUNNING EQUIP., RIH W/ TOTALLY 71 JTs 9-5/8" CSG (53.5#, L-80, TPCQ) TO 776 M TILL M.N |  | -2413
WellA | 2020-01-20 | 2413 | 12.25 | 147 | CONT. RIH W/ TOTALLY 83 JTs 9-5/8" CSG (53.5#, L-80, TPCQ) & 113 JTs 9-5/8" CSG (47#, T-95, TPCQ) F/ 776 TO 2185 M WHILE CIRC @ 1876 M (13 5/8" CSG SHOE) TILL M.N |  | -2413
WellA | 2020-01-21 | 2413 | 12.25 | 148 | CONT. RIH TO 2413 M, TAG BTM, POOH TO 2412 M (9 5/8" CSG SHOE), PERFORM 9-5/8" CMT JOB, INSTALL 13-5/8" * 9-5/8" CSG SLIPS HGR, WOC TO GET HARD TILL M.N |  | -2413
WellA | 2020-01-22 | 2413 | 12.25 | 149 | WOC TO GET HARD, SLACK OFF STRG WEIGHT, PICK UP BOP STACK, DRESS & BEVEL 9-5/8" CSG NECK, INSTALL 13-5/8", 5K * 11", 10K DSA + 11" * 11", 10K T.H.S & TEST P-SEALS TILL M.N |  | -2413
WellA | 2020-01-23 | 2413 | 12.25 | 150 | N/UP 13-5/8", 10K BOP STACK. CHANGE TOP RAMS. CONNECT CHOKE & KILL LINE, TEST FOUR T.H.S GATE VALVES, INSTALL 11" PLUG TESTER & WORK ON RECTIFY LEAKAGES TILL M.N |  | -2413
WellA | 2020-01-24 | 2413 | 12.25 | 151 | CONT WORK ON RECTIFY LEAKAGES, PERFORM 13-5/8", 10K BOP TEST AS NIDC POLICY. L/D 12 JTs 8-1/2" DC & L/D 15 JTs 5" HWDP. RIH W/ B.BIT#13 NEW (K.DREAM, 1512743JH, 517, 3*18/32") TO 37 M TILL M.N |  | -2413
WellA | 2020-01-25 | 2413 | 12.25 | 152 | CONT RIH W/ B.BIT#13 NEW (K.D,517, 3*18) F/ 37 TO 2367 M, TAKE WEIGHT, CONT D/O PLUGS, F.C & MED. CMT F/ 2367 TO 2408 M, DICPLACE MUD, CONT D/OUT MED CMT F/ 2408 TO 2411 M TILL M.N |  | -2413
WellA | 2020-01-26 | 2427 | 8.5 | 153 | CONT D/OUT MED CMT F/ 2411 TO 2412 M, DRLG 8-1/2" HOLE SEC. F/ 2412 TO 2427M W/ NL-NG , CIRC BTM S UP, POOH FOR SCRAPPER TRIP F/ 2427 TO 1700 M W/ NL-NG TILL M.N |  | -2427
WellA | 2020-01-27 | 2427 | 8.5 | 154 | POOH FOR SCRAPPER TRIP F/ 2427 TO SURF W/ NL-NG, RIH W/ SAME BIT & 9-5/8" SCRAPPER TO 1200 M WHILE SCRAP EACH STD TWO TIMES TILL M.N |  | -2427
WellA | 2020-01-28 | 2427 | 8.5 | 155 | RIH F/ 1200 TO 2408 M WHILE SCRAP EACH STD TWO TIMES, PUMP HI-VIS PILL, CIRC BTM S UP, POOH TO SURF., R/UP LOG., RIH W/ ( CDR, GR) TO 2000 M WHHLE CIRC CWHD NL-NG TILL M.N |  | -2427
WellA | 2020-01-29 | 2427 | 8.5 | 156 | RIH W/LOGGING TOOLS, RUN #1 TO 2427M, L/UP TO 1800M, POOH TO SURF., L/D CDR/GR. P/U RUN # 2, RIH TO 2408M, L/UP TO 1700M, POOH TO SURF., L/D LOGGING TOOLS. INSTALL PLUG TESTER, PERFORM BOP TEST AS NIOC POLICY, TEST HYDRILL "OK", TEST TOP RAMS W/7500PSI, OBS LEAKAGE IN BONNET SEAL RAMS, WAIT ON REC. RTTS TOOLS, RIH W/5" DP TO 464M, P/U RTTS TOOLS TILL M.N |  | -2427
WellA | 2020-01-30 | 2427 | 8.5 | 157 | SET RTTS PACKER, WORK ON BOP STACK LEAKAGE, BOP TEST "OK", REMOVE RTTS, P/U 8-1/2" NEW PDC BIT W/BHA#29 TO 2412M, INSTALL ROTATIN HEAD, RIH TO 2427M(BTM) WHILE F/U STRG EACH 10STD, NL-NG TILL M.N |  | -2427
WellA | 2020-01-31 | 2469 | 8.5 | 158 | RESUME DRLG FM F/2427 TO 2469M, NL-NG TILL M.N |  | -2469
WellA | 2020-02-01 | 2508 | 8.5 | 159 | CONT. DRLG FM F/2469 TO 2485M, CHECK HOLE COND., GET SURVEY, CONT. DRLG TO 2508M, NL-NG TILL M.N |  | -2508
WellA | 2020-02-02 | 2559 | 8.5 | 160 | CONT. DRLG FM F/2508 TO 2536M, CHECK HOLE COND., GET SURVEY, CONT. DRLG TO 2559M, NL-NG TILL M.N |  | -2559
WellA | 2020-02-03 | 2613 | 8.5 | 161 | CONT. DRLG FM F/2559 TO 2613M WHILE PUMP 20BBL HI-VIS PILL PERIODICALLY, NL-NG TILL M.N |  | -2613
WellA | 2020-02-04 | 2633 | 8.5 | 162 | CONT. DRLG FM F/2613 TO 2615M WHILE PUMP 20BBL HI-VIS PILL PERIODICALLY, GET SURVEY @ 2598M, CONT. DRLG FM WHILE INC. MW TO 68PCF GRADUALLY, PUMP 30 BBL LCM PILL PERIODICALLY, 8-10 BPH LOSS TILL M.N |  | -2633
WellA | 2020-02-05 | 2640 | 8.5 | 163 | CONT. DRLG FM F/2633 TO 2637M, DISP. WELL W/70PCF MUD, CONT. DRLG, DUE TO INC. LOSS, PUMP & SPOT 100BBL LCM PILL, POOH TO SHOE, CIRC. & CHECK FM LOSS, RIH TO BTM, CONT. DRLG TO 2640M TILL M.N |  | -2640
WellA | 2020-02-06 | 2657 | 8.5 | 164 | CONT. DRLG F/2640 TO 2643M, INC. LOSS TO 20BPH, CONT. DRLG W/BY PASS SYS. TO 2646M, OBS 10-80BPH LOSS. SPOT 100BBL LCM PILL, POOH TO 2500M, RUN BACK TO BTM, CONT. DRLG TO 2657M WHILE ADD. 5LB/BBL LCM TO SYS. & DEC. MW TO 68PCF , 18-20BPH LOSS TILL M.N |  | -2657
WellA | 2020-02-07 | 2657 | 8.5 | 165 | DUE TO LOW ROP, SPOT 100BBL LCM PILL 15LB/BBL, POOH TO SURF., OBS WELL 3STAGE, 4BPH LOSS, L/D BIT, TEST TUBING HANGER, PERFORM BOP TEST AS NIOC POLICY, HYDRILL & CHOKE MANIFOLD TEST IS "OK", OBS LEAKAGE IN BONNET SEAL ALL RAMS, INSTALL TUBING HANGER & TEST IT "OK", WAIT ON REC. BONNET SEAL, CIRC. W/ANN. 2-14BPH LOSS TILL M.N. |  | -2657
WellA | 2020-02-08 | 2657 | 8.5 | 166 | WAIT ON REC. BOP BONNET SEAL, WORK ON BOP STACK, CONT. BOP TEST, TEST IS"OK", P/U 8-1/2" NEW PDC BIT & SAME BHA TO 100M, 14-16BPH LOSS TILL M.N |  | -2657
WellA | 2020-02-09 | 2657 | 8.5 | 167 | CONT. RIH W/8-1/2" NEW PDC BIT TO 800M WHILE F/U STRG EACH 10STD, PLUG STRG, WORK ON UNPLUG "NO SUCC"., POOH TO SURF. UNPLUG STRG, RUN BACK TO 2650M, 15-20BPH LOSS TILL M.N |  | -2657
WellA | 2020-02-10 | 2700 | 8.5 | 168 | RESUME DRLG F/2657 TO 2700M WHILE PUMP 30BBL LCM PILL EACH 5M, 15-5BPH LOSS., COND. TRIP TO 2550M, RUN BACK TO BTM, GOOD COND. SPOT 80BBL HI-VIS PILL, RUN MULTI SHUT & GET SURVEY @ 2695M TILL M.N |  | -2700
WellA | 2020-02-11 | 2750 | 8.5 | 169 | L/D MULTI SHUT TOOLS (RUN#4), CONT. DRLG W/BY PASS SYS. F/2700 TO 2731M WHILE INC. KCL SYS. TO 3%, 4-8 BPH LOSS., CONT. DRLG F/2731 TO 2750M WHILE SHAKER OUT MUD SYS & INC. KCL SYS. TO 6%, 4-8 BPHLOSS., POOH TO 2680, GOOD COND. RUN BACK TO BTM, GET SURVEY @ 2750M TILL M.N |  | -2750
WellA | 2020-02-12 | 2784 | 8.5 | 170 | TAKE SURVEY @ 2740M (INC: 4.8DEG), L/D MULTI SHUT TOOLS, CONT. DRLG FORM. F/ 2750 TO 2784 M WHILE PUMP 30 BBL LCM PILL EACH JOINT W/ 8-10 BPH LOSS TILL M.N |  | -2784
WellA | 2020-02-13 | 2823 | 8.5 | 171 | CONT. DRLG FORM. F/ 2784 TO 2804 M, R/U MULTI SHUT RUNNING EQUIP. & TAKE SURVEY @ 2797M (INC: 5 DEG), L/D MULTI SHUT TOOLS, CONT. DRLG FORM. F/ 2804 TO 2823 M WHILE TILL M.N |  | -2823
WellA | 2020-02-14 | 2848 | 8.5 | 172 | CONT. DRLG FORM. F/ 2823 TO 2848 M WHILE INC. MW F/ 70 TO 71 PCF, POOH F/ 2848 TO 2740 M TO CHECK WELL COND. FOR TAKE SURVEY WHILE W&R THIS INTERVAL SEVERAL TIMES TILL M.N |  | -2848
WellA | 2020-02-15 | 2869 | 8.5 | 173 | CONT. DRLG FORM. F/ 2848 TO 2869 M W/ 8-12 BPH LOSS WHILE INC. MW F/ 71 TO 73PCF @ TWO STEP & PUMP HI-VIS & LCM PILL PERIODICALLY TILL M.N |  | -2869
WellA | 2020-02-16 | 2901 | 8.5 | 174 | CONT. DRLG FORM. F/ 2869 TO 2901 M W/ 8-12 BPH LOSS WHILE PUMP HI-VIS & LCM PILL PERIODICALLY TILL M.N |  | -2901
WellA | 2020-02-17 | 2911 | 8.5 | 175 | CONT. DRLG FORM. F/ 2901 TO 2911 M W/ 10-14 BPH LOSS WHILE SUDDENLLY INC. RETURN MUD, CLOSE THE WELL, MONITOR SICP & SIDPP, KILL THE WELL W/ 76 PCF MUD, OPEN THE WELL. SPOT 140 BBL HI VIS LCM PILL @ 2911 M (BTM), POOH FOR BOP TEST F/ 2911 TO 2600 M WHILE C.W.H W/ NL-NG TILL M.N |  | -2911
WellA | 2020-02-18 | 2911 | 8.5 | 176 | CONT. POOH FOR BOP TEST F/ 2600 TO 2412 M, OBS WELL W/ 3 BPH GAIN, CLOSE THE WELL, CIRC MUD WHILE INC MW F/ 76 TO 79 PCF, RIH TO 2911 M(BTM), INC MW F/ 79 TO 81 PCF, WHILE WAITING FOR NIDC DFSM CIRC MUD TILL M.N |  | -2911
WellA | 2020-02-19 | 2911 | 8.5 | 177 | WHILE WAITING FOR NIDC DFSM CIRC MUD, CIRC MUD WHILE INC MW F/ 81 TO 83 PCF, POOH FOR BOP TEST F/ 2911 TO 1600 M WHILE OBS WELL @ 9-5/8" CSG SHOE W/ 8 BPH LOSS TILL M.N |  | -2911
WellA | 2020-02-20 | 2911 | 8.5 | 178 | CONT POOH FOR BOP STACK PRESS TEST F/ 1600 TO SURF. WHILE CIRC C.W.H W/ 2-4 BPH LOSS, PERFORM BOP TEST WHILE OBS LEAKAGE & WORK ON RECTIFY LEAKAGES TILL M.N |  | -2911
WellA | 2020-02-21 | 2911 | 8.5 | 179 | WORK ON RECTIFY TOP, BTM & SHEAR RAMS BONNET SEALS LEAKAGES WHILE CIRC C.W.H THROUGH T.H.S SIDE VALVES W/ 4-16 BPH LOSS TILL M.N |  | -2911
WellA | 2020-02-22 | 2911 | 8.5 | 180 | CONT WORK ON RECTIFY TOP, BTM & SHEAR RAMS BONNET SEALS LEAKAGES, NO SUCC. RIH W/ 6-1/8" C.CUT BIT FOR PERFORM MAGNESET & CMT PLUG JOB TO 2412 M W/ 16-50 BPH LOSS TILL M.N |  | -2911
WellA | 2020-02-23 | 2911 | 8.5 | 181 | CONT RIH W/ 6-1/8" C.CUT BIT TO 2560, SPOT 100 BBL LCM PILL, POOH TO 2130 M, SLOW CIRC MUD, MUD LOSS INC. TO 12BPH AFTER 11 HRs, RUN BACK TO 2550 M & SPOT 100 BBL LCM PILL AGAIN TILL M.N |  | -2911
WellA | 2020-02-24 | 2911 | 8.5 | 182 | WAITING FOR NIDC DFMD DUE TO MUD MATERIAL SHORTAGE WHILE CONT SLOW (F.R: 100 GPM) CIRC MUD W/ 0-6 BPH LOSS TILL M.N. |  | -2911
WellA | 2020-02-25 | 2911 | 8.5 | 183 | DUE TO INC MUD LOSS RIH TO 2550 M & SPOT 100 BBL LCM PILL, POOH TO 2150 M & SLOW CIRC MUD. MUD MATERIAL RECEIVED. PERFORM MAGNESET PLUG JOB. WAIT ON MAGNESET TO GET HARD TILL M.N. |  | -2911
WellA | 2020-02-26 | 2911 | 8.5 | 184 | WAITING FOR NIDC DRILLING MOBILE TOOLS DEPT. DUE TO BOP LEAKAGE WHILE WAIT ON MAGNESET PLUG TO GET HARD WHILE SLOW CIRC. MUD @ 1850M W/ 100 GPM, W/ 2-0 BPH LOSS TILL M.N |  | -2911
WellA | 2020-02-27 | 2911 | 8.5 | 185 | WAIT ON MAGNESET PLUG, RIH F/1850 TO 2250M, C.B.U, RIH TO 2270M, CONFIRM PLUG @ 2270M W/500LB., C.B.U, R/U CMT LINE & TEST IT "OK"., CMT PLUG @ 2260M, POOH 18 STD TO 1740M, WAIT ON CMT TO GET HARD WHILE SLOW CIRC., NL-NG TILL M.N |  | -2911
WellA | 2020-02-28 | 2911 | 8.5 | 186 | DUE TO CHANGE BOP STACK, POOH F/2122 TO SURF., L/D 6-1/8" C.CUT, REMOVE W.BUSHING, INSTALL TUBING HANGER, WORK ON CHANGE BOP STACK TILL M.N |  | -2911
WellA | 2020-02-29 | 2911 | 8.5 | 187 | CONT. N/DOWN 13-5/8" 10K OLD BOP STACK, N/U 13-5/8" 10K NEW BOP STACK TILL M.N |  | -2911
WellA | 2020-03-01 | 2911 | 8.5 | 188 | CONT. N/U 13-5/8" BOP STACK, BODY TEST, OBS LEAKAGE IN BONNET SEAL, WORK ON LEAKAGE TILL M.N |  | -2911
WellA | 2020-03-02 | 2911 | 8.5 | 189 | CONT.WORK ON 13-5/8" BOP STACK, TEST BTM RAMS "OK", TEST TOP RAMS AGAIN, OBS LEAKAGE IN BONNET SEAL, WORK ON LEAKAGE, SLIP & CUT DRLG LINE, L/D 9JT 6-1/2" DC TILL M.N |  | -2911
WellA | 2020-03-03 | 2911 | 8.5 | 190 | CHANGE TOP RAMS BONNET SEAL, TEST AGAIN TOP, BTM, SHEAR RAMS "OK", RIH W/8-1/2" B.BIT & NEW BHA TO 1600M WHILE F/U STRG EACH 10STD, NL-NG TILL M.N |  | -2911
WellA | 2020-03-04 | 2911 | 8.5 | 191 | CONT. RIH TO 2000M, PUMP DOWN TO 2117M, WASH & REAM TO 2122M, C.B.U, INC. MW TO 90PCF, D/OU CMT F/2122 TO 2156M WHILE PUMP 20BBL HI-VIS PILL PERIODICALLY, NL-NG. |  | -2911
WellA | 2020-03-05 | 2911 | 8.5 | 192 | CONT. D/OUT HARD CMT F/2156 TO 2209M WHILE PUMP 20BBL HI-VIS PILL PERIODICALLYWHILE & WORK ON MUD PUMPS @ SEVERAL TIMES, NL-NG TILL M.N |  | -2911
WellA | 2020-03-06 | 2911 | 8.5 | 193 | CONT. D/OUT HARD CMT F/2209 TO 2255M, WASH DOWN TO 2266M, CIRC. THRU CHOKE, RIH TO 2412M, CIRC. THRU CHOKE, OBS GAS, CONT. CIRC. THRU POORBOY DEGASSER & DEC. MW TO 85PCF., OBS WELL STATIC., CONT RIH TO 2554M, CIRC. MUD, OBS WELL KICK, CIRC. THRU POORBOY DEGASSER, CONT. RIH TO 2696M, CIRC. MUD THRU POORBOY TILL M.N |  | -2911
WellA | 2020-03-07 | 2919 | 8.5 | 194 | CIRC. MUD @ 2696 M, BURRNING GAS & POORBOY DEGASSER, RIH TO 2775 M, TOOK WEIGHT, REAMING "NO SUCC", SHUT THE WELL & CIRC. OUT GAS AS POOR BOY DEGASSER & BURNING IT, W & R TO 2905M, SHUT THE WELL & CIRC. OUT GAS & BURNING IT W/POORBOY DEGASSER, W & R TO 2911 M(BTM), RESUME DRLG FM F/2911 TO 2919 M WHILE INC MW TO 86PCF, 15-20BPH LOSS TILL M.N |  | -2919
WellA | 2020-03-08 | 2919.5 | 8.5 | 195 | CONT. DRLG TO 2919.5M, C.B.U, SPOT 60BBL HI-VIS PILL, POOH TO 2650M(REAMING @ 2811M), SPOT 80BBL LCM PILL 20LB/BBL, POOH TO 2350M, OBS WELL, 7-8BPH LOSS, CONT. POOH TO SURF. OBS WELL @ BHA "STATIC", CHECK THE BIT "OK", RIH W/SAME BIT & BHA (ADD. S.STAB) TO 1400M, 4-5BPH LOSS TILL M.N |  | -2919.5
WellA | 2020-03-09 | 2919.5 | 8.5 | 196 | CONT. RIH F/1400 TO 2412 M, INSTALL R.HEAD, RIH TO 2731 M W/GOOD COND., HARD W & REAM TO 2919.5 M WHILE WORK ON MUD PROPERTIES & INC. MW TO 87 PCF, 8-10 BPH LOSS. CHECK HOLE COND. F/BTM TO 2750M W/HARD B.REAM, CONT. POOH TO 2700 M W/GOOD COND., 8-10 BPH LOSS TILL M.N |  | -2919.5
WellA | 2020-03-10 | 2919.5 | 8.5 | 197 | CONT. POOH F/2700 TO 2412M W/GOOD HOLE COND., OBS WELL 8 BPH LOSS. RUN BACK TO 2720M, TOOK WEIGHT, HARD WASH & REAM TO 2919.5M 10-15 BPH LOSS, PUMP 20 BBL PHPA PILL EACH STD, DUE TO INC. MUD LOSS, SPOT 50 BBL LCM PILL 10 LB/BBL, B.REAM TO 2678M, SPOT 100 BBL LCM PILL 20LB/BBL, POOH TO 2267 M, OBS WELL 8 BPH LOSS, RUN BACK TO 2730M, TOOK WEIGHT TILL M.N |  | -2919.5
WellA | 2020-03-11 | 2919.5 | 8.5 | 198 | HARD WASH & REAM F/ 2730 TO 2919.5M W/10-15 BPH LOSS. INC MW TO 88 PCF. B.REAM TO 2730M, POOH F/ 2730 TO 2670M, SPOT 100 BBL LCM PILL 20LB/BBL, POOH TO 2250 M. OBS WELL 2-4 BPH LOSS. RUN BACK TO 2772M, TOOK WEIGHT, SOFT TO HARD WASH & REAM TO 2820M W/ 6-10 BPH LOSS TILL M.N |  | -2919.5
WellA | 2020-03-12 | 2919.5 | 8.5 | 199 | HARD WASH & REAM F/ 2820 TO 2850M. INC MUD LOSS TO 40 BPH. B.REAM TO 2785M, POOH F/ 2785 TO 2670M, SPOT 100 BBL LCM PILL 20LB/BBL, POOH TO 2250 M. SPOT 60 BBL LCM PILL. POOH TO 2000M, SLOW CIRC MUD. RIH TO 2200 M. SPOT 50 BBL LCM PILL. POOH TO 2000 M & SLOW CIRC MUD W/ 8-10 BPH LOSS TILL M.N |  | -2919.5
WellA | 2020-03-13 | 2919.5 | 8.5 | 200 | SLOW CIRC MUD W/ 8-16 BPH LOSS WHILE SPOT 50 BBL LCM PILL @2412 M( 9-5/8" CSG SHOE) & CUT MW F/ 88 TO 87 PCF TILL M.N |  | -2919.5
WellA | 2020-03-14 | 2919.5 | 8.5 | 201 | SLOW CIRC MUD W/ 8-20 BPH LOSS WHILE SPOT LCM PILL PERIODICALLY & CUT MW F/ 87 TO 86 PCF TILL M.N |  | -2919.5
WellA | 2020-03-15 | 2919.5 | 8.5 | 202 | SPOT 75 BBL LCM PILL @ 2090 M. POOH TO 1750 M. SLOW CIRC MUD W/ 8-10 BPH LOSS. RIH TO 2000 M. SPOT 50 BBL HI-VIS LCM PILL. POOH TO 1700M & OBS WELL W/ 0-2 BPH LOSS. POOH TO SURF. BOP STACK PRESS TEST IN PROGRESS TILL M.N |  | -2919.5
WellA | 2020-03-16 | 2919.5 | 8.5 | 203 | PERFORM 13-5/8", 10 K BOP STACK PRESS TEST AS NIDC POLICY, RIH W/ 8-1/2" B.BIT#13RR4 & 8-3/8" S.STAB @ 20M TO 2350 M, SLOW CIRC MUD WHILE SPOT PILL PERIODICALLY TILL M.N |  | -2919.5
WellA | 2020-03-17 | 2919.5 | 8.5 | 204 | SLOW CIRC MUD W/ 8-1/2" B.BIT#13RR4 & 8-3/8" S.STAB @ 20M WHILE SPOT HI-VIS LCM PILL (15 LB F + 10 LB M) PERIODICALLY TILL M.N |  | -2919.5
WellA | 2020-03-18 | 2919.5 | 8.5 | 205 | SLOW CIRC MUD @ 2000 M W/ 2-6 BPH LOSS, RECEIVED MUD MATERIAL, RIH TO 2412 M, INC SYSTEM MUD VIS TO 50, BY-PASS SHAKER & ADD 10 LB OYSTERSHEL (F&M) TO SYSTEM MUD IN PROGRESS TILL M.N |  | -2919.5
WellA | 2020-03-19 | 2919.5 | 8.5 | 206 | BY-PASS SHAKER & ADD 10 LB OYSTERSHEL (F&M) TO SYSTEM MUD,RIH TO 2720 M WASH DOWN, TAKE WEIGHT, CONT RIH W/ W&R TO 2919.5 M, CIRC BTM S UP, POOH W/ B.REAM TO 2780 M TILL M.N |  | -2919.5
WellA | 2020-03-20 | 2919.5 | 8.5 | 207 | POOH W/ B.REAM TO 2720 M, CONT POOH TO 2600 M W/ GOOD HOLE COND, RUN BACK TO 2727 M, TAKE WEIGHT, CONT RIH W/ W&R TO 2919.5 M, POOH W/ B.REAM TO 2760 M TILL M.N |  | -2919.5
WellA | 2020-03-21 | 2919.5 | 8.5 | 208 | POOH W/ B.REAM TO 2730 M, CONT POOH TO 2600 M W/ GOOD HOLE COND, RUN BACK TO 2730 M, TAKE WEIGHT, CONT RIH W/ W&R TO 2815 M, POOH FOR CMT PLUG JOB TO 700 M TILL M.N |  | -2919.5
WellA | 2020-03-22 | 2919.5 | 8.5 | 209 | POOH FOR CMT PLUG JOB TO SURF., RIH W/ 6-1/8" C.CUT BIT TO 1595 M, STRG PLUGED, POOH TO 285 M & UNPLUG STRG, RUN BACK TO HOLE W/ 6-1/8" C.CUT BIT F/ 285 TO 1500 M TILL M.N |  | -2919.5
WellA | 2020-03-23 | 2919.5 | 8.5 | 210 | RIH W/ 6-1/8" C.CUT BIT F/1500 TO 2650M, SPOT 50 BBL HI-VIS PILL, POOH TO 2450 M, SHAKER OUT LCM F/ MUD, PERFORM MAGNESET PLUG JOB, WAIT ON MAGNESET WHILE SLOW CIRC MUD@1950M TILL M.N |  | -2919.5
WellA | 2020-03-24 | 2919.5 | 8.5 | 211 | WAIT ON MAGNESET FOR 15 HRS, RIH W/ 6-1/8" C.CUT BIT F/1950 TO 2300M, CIRC BTM S UP, PERFORM CMT PLUG #1 JOB @ 2300M, POOH TO 1700M, CLOSE THE WELL, APPLY 100 PSI PRESS & W.O.C TILL M.N |  | -2919.5
WellA | 2020-03-25 | 2919.5 | 8.5 | 212 | WAIT ON CMT TO GET HARD, OPEN THE WELL & RUN BACK F/ 1700 TO 2124 M, CONFIRM TOP OF CMT PLUG#1 @ 2124 M. CIRC BTM S UP, POOH F/ 2124 M TO SURF., L/D 6 1/8" C.CUT BIT, RIH W/ 8-1/2" USED B.BIT TO 2000 M, SCRAPE F/ 2000 TO 2120 M TILL M.N. |  | -2919.5
WellA | 2020-03-26 | 2919.5 | 8.5 | 213 | CIRC BTM S UP, POOH W/ 9 5/8" SCRAPER F/ 2120 M TO SURF., RIH W/ 9 5/8" DRY TEST TOOLS & FOLLOWED BY 5" DPs TO 1600 M WHILE F/UP STRG EVERY 5 STDs W/SALT WATER (75 PCF) AS CUSHION FLUID TILL M.N. |  | -2919.5
WellA | 2020-03-27 | 2919.5 | 8.5 | 214 | CONT. RIH W/ 9 5/8" DRY TEST TOOLS F/1600 TO 2090 M, SET PACKER @ 2086 M, OPEN THE WELL FOR 3 HRS W/OUT OBS BUBBLE, CLOSE THE WELL BY D.C.I.P VALVE FOR 6 HRS, DROP THE BAR & CONDUCT REV. CIRC. THRU REVERSING SUB & DURING THAT GET 75 PCF SALT WTR, UNSET PACKER, PULL OUT 9 5/8" DST TOOLS F/2090 TO 600 M TILL M.N. |  | -2919.5
WellA | 2020-03-28 | 2919.5 | 8.5 | 215 | CONT. PULL OUT 9 5/8" DST TOOLS F/600 M TO SURF. & L/D IT, RIH W/ 6-1/8" C.CUT BIT TO 1800 M, CIRC. MUD, PERFORM CMT PLUG #2 JOB @ 1800 M, POOH TO 1220 M, CLOSE THE WELL, APPLY 100 PSI PRESS & W.O.C TILL M.N. |  | -2919.5
WellA | 2020-03-29 | 2919.5 | 8.5 | 216 | WAIT ON CMT, RUN BACK TO HOLE W/ 6-1/8" C.CUT BIT TO 1657 M, TAKE WEIGHT @ 1657 M, APPLY 3-4 KLBs WEIGHT W/ 350 GPM, NOT WASH, CIRC BTM S UP, POOH F/ 1657 TO 300 M WHILE L/D TOTALLY 150 JTs 5" DP, RIH F/ 300 TO 1657 M, CIRC. MUD WHILE WORK ON RHEOLOGY AND ADD H2S SCAVENGER & CORROSION INHIBITOR AS PROGRAM TILL M.N. |  | -2919.5
WellA | 2020-03-30 | 2919.5 | 8.5 | 217 | POOH W/ 6-1/8" C.CUT BIT TO SURF. WHILE L/D TOTALLY 330 JTs 5" DP + 15 JTs 5" H.W.D.P + 12 JTs 6 1/2" DC + 30 JTs 3 1/2" DP AND L/D 6 1/8" C.CUT BIT, INSTALL TUBING HANGER INSIDE T.H.S. (TWO-WAY B.P.V INTO TUBING HANGER), TEST W/ 4500 PSI @ 15 MIN, OK. TILL M.N. |  | -2919.5
WellA | 2020-03-31 | 2919.5 | 8.5 | 218 | N/D 13 5/8"-10K BOP STACK TILL M.N. |  | -2919.5
WellA | 2020-04-01 | 2919.5 | 8.5 | 219 | CONT. N/D 13 5/8"-10K BOP STACK, N/UP 11"*11"-10K BTM MASTER VALVE IN PROGRESS TILL M.N. |  | -2919.5
WellA | 2020-04-02 | 2919.5 | 8.5 | 220 | N/UP 11"*11"-10K BTM MASTER VALVE, TRY TO TEST P-SEAL W/ 7000 PSI AT SEVERAL TIMES NO SUCC., N/DOWN BTM MASTER VALVE AND CHECK IT, AGAIN N/UP 11"*11"-10K BTM MASTER VALVE, TEST P-SEAL W/ 7000 PSI OK., TSET BTM MASTER VALVE W/ 7000 PSI OK., CLOSE BTM MASTER VALVE TILL M.N. |  | -2919.5
WellA | 2020-04-03 | 2919.5 | 8.5 | 221 | TRANSFER DRLG FLUID TILL M.N. |  | -2919.5
WellA | 2020-04-04 | 2919.5 | 8.5 | 222 | SEND 9 LOAD DRLG FLUID 86 PCF, RELEASE RIG @ 19:00 O CLOCK, TEAR OUT THE RIG TILL M.N. |  | -2919.5
WellB | 2020-05-03 | 35 | 36 | 1 | R/U 100%, SPUD THE RIG @ 99.02.14, 00:00 O.CLOCK, CIRC. MUD, START DRLG FM F/13 TO 35M, NL-NG TILL M.N |  | -35
WellB | 2020-05-04 | 89 | 36 | 2 | CONT. DRLG F/35 TO 89M, NL-NG WHILE WORK ON MUD PUMP & STAND PIPE MANIFOLD TILL M.N |  | -89
WellB | 2020-05-05 | 107 | 36 | 3 | CONT. DRLG F/89 TO 107M (30" CSG POINT), NL-NG, RUN TOTCO SURVEY & 100M, INC:0.75DEG, POOH TO SURF., L/D 26" BIT. P/U 26" BIT & ... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-06 | 107 | 36 | 4 | CONT. ENLARGE HOLE W/ 26" USED R.BIT#1RR1(K.D, 115, 3*20+ C.J 18) & 36" HOLE OPENER F/ 23.5 TO 34 M W/ NL-NG TILL M.N |  | -107
WellB | 2020-05-07 | 107 | 36 | 5 | CONT. ENLARGE HOLE W/ 26" USED R.BIT#1RR1(K.D, 115, 3*20+ C.J 18) & 36" HOLE OPENNER F/ 34 TO 41 M W/ NL-NG WHILE CHANGE HOLE OP... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-08 | 107 | 36 | 6 | CONT. ENLARGE HOLE W/ 26" USED R.BIT#1RR1(K.D, 115, 3*18+ C.J 16) & 36" HOLE OPENNER F/ 41 TO 48.5 M W/ NL-NG WHILE CHANGE HOLE ... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-09 | 107 | 36 | 7 | CONT. ENLARGE HOLE W/ 26" USED R.BIT#1RR1(K.D, 115, 3*18+ C.J 16) & 36" HOLE OPENNER F/ 48.5 TO 62.5 M W/ NL-NG TILL M.N |  | -107
WellB | 2020-05-10 | 107 | 36 | 8 | CONT. ENLARGE HOLE F/ 62.5 TO 72 M W/ NL-NG, POOH TO SURF, RIH W/ C.CUT BIT TO 105 M. PERFORM CMT PLUG JOB. POOH TO SURF. RIH W/... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-11 | 107 | 36 | 9 | CONT. RIH TO 67M, W.O.C TO GET HARD, D/OUT HARD CMT F/ 67 TO 72M, POOH TO SURF., RUN 6 JTS 30" CSG TO 72 M, RIH W/ 5" STINGER TO... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-12 | 107 | 36 | 10 | W.O.C TO GET HARD, ROUGH CUT 42" C.PIPE & 30" CSG. DRESS & BEVEL 30" CSG. INSTALL 30" FLANG (WELD TYPE, 1 K). N/UP 30" DRILLING ... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-13 | 107 | 36 | 11 | N/UP 30" DRILLING SPOOL & 30" HI-DRILL (1 K), TEST W/ 250 PSI,OK. RIH W/ 26" R.BIT #1RR4 & S.STAB @20 M TO 60M, WORK ON INSTALL ... <Preview truncated at 128 characters> |  | -107
WellB | 2020-05-14 | 119 | 26 | 12 | INSTALL TDS HYDRAULIC IBOP & TEST IT, RIH TO 66 M, TAKE WEIGHT, D/OUT CMT & SHOE W/ 26" R.BIT #1RR4 & S.STAB @20 M TO 107M, DRLG... <Preview truncated at 128 characters> |  | -119
WellB | 2020-05-15 | 152 | 26 | 13 | CONT. DRLG FORM W/ 26" R.BIT #1RR4 & S.STAB @20 M F/ 119 TO 152 M W/ NL-NG, RUN TOTCO, INC: 0.25 DEG., POOH TO SURF & CHECK BIT,... <Preview truncated at 128 characters> |  | -152
WellB | 2020-05-16 | 203 | 26 | 14 | CONT. RIH W/ 26" R.BIT#1RR5 & BHA#4 TO 152 M, DISPLACE HOLE MUD, CONT. DRLG FORM W/ 26" R.BIT #1RR4 & S.STAB @20M & 30M F/ 152 T... <Preview truncated at 128 characters> |  | -203
WellB | 2020-05-17 | 260 | 26 | 15 | CONT. DRLG FORM W/ 26" R.BIT #1RR4 & S.STAB @20M & 30M F/ 203 TO 260M W/ NL-NG WHILE RUN TOTCO SURVEY @244 M, RESULT INC.: 0.75 ... <Preview truncated at 128 characters> |  | -260
WellB | 2020-05-18 | 280 | 26 | 16 | CIRC BTM S UP, POOH TO SURF., CHANGE BIT, RIH TO 260 M, CONT. DRLG FORM W/ 26" R.BIT#2 USED & S.STAB @20M & 30M F/ 260 TO 280M W... <Preview truncated at 128 characters> |  | -280
WellB | 2020-05-19 | 290 | 26 | 17 | CONT. DRLG FORM F/ 280 TO 290M W/ NL-NG, STOP DRLG DUE TO HIGH TRQ, POOH TO SURF. CHECK BIT OK, CHANGE NOZZLES, RIH W/ SAME BIT... <Preview truncated at 128 characters> |  | -290
WellB | 2020-05-20 | 333 | 26 | 18 | CONT. DRLG FM F/ 290 TO 333M, NL-NG TILL M.N |  | -333
WellB | 2020-05-21 | 368 | 26 | 19 | CONT. DRLG FM F/ 333 TO 368M, NL-NG, RUN TOTCO SURVEY @ 349M, RESULT INC. 1 DEG, WORK ON DIESEL GENERATOR # 3 TILL M.N |  | -368
WellB | 2020-05-22 | 379.5 | 26 | 20 | CONT. DRLG FM F/ 368 TO 379.5M, NL-NG, FAILURE TDS, DUE TO CHANGE BIT POOH TO SURF., L/D 26" R.BIT (BALLED UP BIT), P/U NEW 26"... <Preview truncated at 128 characters> |  | -379.5
WellB | 2020-05-23 | 430 | 26 | 21 | CONT. DRLG FM F/ 379.5 TO 430M, NL-NG TILL M.N |  | -430
WellB | 2020-05-24 | 467 | 26 | 22 | CONT. DRLG FM F/ 430 TO 452M, RUN TOTCO SURVEY, RESULT INC.:1.25DEG, CONT. DRLG TO 467M WHILE INC. MW TO 73PCF, NL-NG TILL M.N |  | -467
WellB | 2020-05-25 | 495 | 26 | 23 | CONT. DRLG FM F/ 467 TO 495M WHILE INC. MW TO 75PCF, NL-NG TILL M.N |  | -495
WellB | 2020-05-26 | 531 | 26 | 24 | CONT. DRLG FM F/ 495 TO 531M, NL-NG TILL M.N |  | -531
WellB | 2020-05-27 | 545 | 26 | 25 | CONT. DRLG FM F/ 531 TO 545M (20" CSG POINT), RUN TOTCO SURVEY, RESULT INC. 2 DEG, POOH TO SURF. CHECK BHA, RUN BACK TO 70M, WA... <Preview truncated at 128 characters> |  | -545
WellB | 2020-05-28 | 545 | 26 | 26 | INC. MW TO 80PCF, SPOT PILL, POOH TO SURF., L/D BIT & STAB, R/U CSG CREW EQUIP., P/U 20" SHOE + 36 JT 20" CSG TO 436M AS PROGRAM... <Preview truncated at 128 characters> |  | -545
WellB | 2020-05-29 | 545 | 26 | 27 | CONT. RUN 20" CSG TO 545M, TAG BTM, POOH TO 544.5M, CIRC. THRU CSG, RIH W/5 STINGER, STAB IN SHOE, C.B.U, PERFORM CMT JOB AS PR... <Preview truncated at 128 characters> |  | -545
WellB | 2020-05-30 | 545 | 26 | 28 | L/D L.JOINT. N/DOWN 30" BOP STACK, CUT 20" CSG, INSTALL & WELDING 20-3/4" C.H.H 3K, TEST W/500PSI "OK", N/U 20-3/4" 3K BOP STAC... <Preview truncated at 128 characters> |  | -545
WellB | 2020-05-31 | 545 | 26 | 29 | CONT. N/U 20-3/4" BOP STACK, BOP AS NIOC POLICY TILL M.N |  | -545
WellB | 2020-06-01 | 546 | 17.5 | 30 | RIH W/17-1/2" B.BIT & JUNK SUB TO 542.5M(39 JT JT BY JT), D/OUT HARD CMT TO 543M, CSG PRESS TEST W/1200PSI "OK", D/OUT CMT & SHO... <Preview truncated at 128 characters> |  | -546
WellB | 2020-06-02 | 547.6 | 17.5 | 31 | PREPARE MUD 120PCF, DISPLACE MUD IN WELL W/120PCF MUD, FIT TEST W/220PSI "OK", FAILURE 2MOTORS, CIRC. MUD WHILE WORK ON THEM, CO... <Preview truncated at 128 characters> |  | -547.6
WellB | 2020-06-03 | 594 | 17.5 | 32 | CONT RIH W/ 17-1/2" PDC BIT#5 NEW (K.D, KM1952AR, 7*15) & S.STAB@20M F/ 22 TO 547.6 M (BTM), CONT DRLG 17-1/2" HOLE SECTION F/ 5... <Preview truncated at 128 characters> |  | -594
WellB | 2020-06-04 | 681 | 17.5 | 33 | TAKE SURVEY@590M,INC: 1DEG.,CONT DRLG F/ 594 TO 650 M, GET STUCK @633M WHILE BACKREAM, FREE STRG & POOH TO 20" CSG SHOE, INC MW ... <Preview truncated at 128 characters> |  | -681
WellB | 2020-06-05 | 758 | 17.5 | 34 | CHANGE WASH PIPE, CONT DRLG F/ 681 TO 728 M,C.B.U & TAKE SURVEY@716M,INC: 1.75DEG., CONT DRLG F/ 728 TO 758 M WHILE INC MW F/ 12... <Preview truncated at 128 characters> |  | -758
WellB | 2020-06-06 | 805 | 17.5 | 35 | CONT DRLG F/ 758 TO 789 M, STOP DRLG DUE TO DIESEL GENERATORS FAILURE, TURN THEM ON & CONT DRLG F/ 789 TO 805 M / NL-NG TILL M.N |  | -805
WellB | 2020-06-07 | 851 | 17.5 | 36 | CONT DRLG F/ 805 TO 841 M, STOP DRLG DUE TO MUD RHEOLOGY CHANGED, WORK ON MUD PROPERTIES, NO SUCC. CONT DRLG F/ 841 TO 851 M W/ ... <Preview truncated at 128 characters> |  | -851
WellB | 2020-06-08 | 903 | 17.5 | 37 | CONT DRLG F/ 851 TO 863 M, STOP DRLG DUE TO DIESEL GENERATOR#1 FAILURE, POOH TO 20" CSG SHOE & RUN BACK TO 863 M(BTM), CONT DRLG... <Preview truncated at 128 characters> |  | -903
WellB | 2020-06-09 | 916 | 17.5 | 38 | CONT DRLG F/ 903 TO 913 M, RUN TOTCO@890 M, INC. 1.25 DEG. POOH TO SURF. DUE TO MUD MATERIAL SHORTAGE & RIH W/ SAME BIT & SAME B... <Preview truncated at 128 characters> |  | -916
WellB | 2020-06-10 | 994 | 17.5 | 39 | CONT DRLG F/ 916 TO 992 M, STOP DRLG DUE TO DIESEL GENERATOR#3 FAILURE & REPAIR IT, CONT DRLG F/ 992 TO 994 M W/ NL-NG TILL M.N |  | -994
WellB | 2020-06-11 | 1026 | 17.5 | 40 | CONT DRLG F/ 994 TO 1026 M, RUN TOTCO SURVEY @1007 M, RESULT INC. 1.75 DEG, WAITING FOR NIDC DFSM DUE TO MUD MATERIAL SHORTAGE W... <Preview truncated at 128 characters> |  | -1026
WellB | 2020-06-12 | 1026 | 17.5 | 41 | WAITING FOR NIDC DFSM WHILE RIH F/ 544.5 TO 1026 M(BTM), CIRC BTM S UP FOR CHECK BTM HOLE MUD COND., POOH TO 544.5 M & SLOW CIRC... <Preview truncated at 128 characters> |  | -1026
WellB | 2020-06-13 | 1026 | 17.5 | 42 | WAITING FOR NIDC DFSM WHILE RIH F/ 544.5 TO 1026 M(BTM), CIRC BTM S UP FOR CHECK BTM HOLE MUD COND., CONT CIRC MUD TILL M.N |  | -1026
WellB | 2020-06-14 | 1026 | 17.5 | 43 | WAITING FOR NIDC DFSM DUE TO MUD MATERIAL SHORTAGE WHILE SLOW CIRC MUD @544.5 M (20"CSG SHOE) NL-NG TILL M.N |  | -1026
WellB | 2020-06-15 | 1026 | 17.5 | 44 | WAITING FOR NIDC DFSM DUE TO MUD MATERIAL SHORTAGE WHILE SLOW CIRC MUD @544.5 M (20"CSG SHOE) NL-NG TILL M.N |  | -1026
WellB | 2020-06-16 | 1069 | 17.5 | 45 | WHILE WAITING FOR NIDC DFSM SLOW CIRC MUD @544.5 M (20"CSG SHOE), RIH TO 1026M (BTM), CIRC BTM S UP, CONT DRLG FORM. F/ 1026 TO ... <Preview truncated at 128 characters> |  | -1069
WellB | 2020-06-17 | 1126 | 17.5 | 46 | CONT DRLG FORM. F/ 1069 TO 1123M, RUN TOTCO@1113 M, INC.: 1.25 DEG, CONT DRLG FORM TO 1126 M, POOH FOR CHANGE TDS WASH PIPE F/ 1... <Preview truncated at 128 characters> |  | -1126
WellB | 2020-06-18 | 1171 | 17.5 | 47 | CHANGE WASH PIPE, CONT. DRLG F/1126 TO 1137M,0-2 BPH LOSS. FAILURE & CHANGE WASH PIPE, CONT. DRLG TO 1171M, NL-NG TILL M.N |  | -1171
WellB | 2020-06-19 | 1211 | 17.5 | 48 | CONT. DRLG FM F/1171 TO 1211M, WORK ON MUD PUMP SEVERAL TIMES, 0-2BPH LOSS TILL M.N |  | -1211
WellB | 2020-06-20 | 1266 | 17.5 | 49 | CONT. DRLG FM F/1211 TO 1240M, 0-2BPH LOSS, C.B.U, TAKE SURVEY, WORK ON GENERATOR, CONT. DRLG TO 1266M, NL-NG TILL M.N |  | -1266
WellB | 2020-06-21 | 1327 | 17.5 | 50 | CONT. DRLG FM F/1266 TO 1327M, INC. MW TO 134 PCF @ 2STAGE, 0-2 BPH LOSS TILL M.N |  | -1327
WellB | 2020-06-22 | 1374 | 17.5 | 51 | CONT. DRLG FM F/1327 TO 1374M, WHILE WORK ON MUD PROPERTIES, 4-6BPH LOSS TILL M.N |  | -1374
WellB | 2020-06-23 | 1403.4 | 17.5 | 52 | CONT. DRLG FM F/1374 TO 1403.4M (13-5/8" CSG POINT), WHILE WORK ON MUD PROPERTIES, 4-6BPH LOSS, DUE TO SHORTAGE MUD MATERIAL FOR... <Preview truncated at 128 characters> |  | -1403.4
WellB | 2020-06-24 | 1403.4 | 17.5 | 53 | CONT. PREPARE NEW MUD 134PCF, CIRC. & ADD TO MUD SYS. & WORK ON MUD REHOLOGY, DUE TO CHECK HOLE COND. POOH F/1403 TO 1300M W/GOO... <Preview truncated at 128 characters> |  | -1403.4

## Sheet1
Depth(m)
19 | -19
87 | -87
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
135 | -135
161 | -161
210 | -210
282 | -282
296 | -296
350 | -350
425 | -425
475 | -475
529 | -529
529 | -529
551 | -551
603 | -603
642 | -642
667 | -667
714 | -714
746 | -746
756 | -756
798 | -798
848 | -848
866 | -866
873 | -873
916 | -916
932 | -932
932 | -932
973 | -973
998 | -998
998 | -998
998 | -998
998 | -998
998 | -998
998 | -998
998 | -998
1006 | -1006
1023 | -1023
1023 | -1023
1023 | -1023
1023 | -1023
1078 | -1078
1149 | -1149
1206 | -1206
1232 | -1232
1289 | -1289
1289 | -1289
1295 | -1295
1321 | -1321
1358 | -1358
1358 | -1358
1358 | -1358
1358 | -1358
1378 | -1378
1417 | -1417
1495 | -1495
1539 | -1539
1594 | -1594
1629 | -1629
1632 | -1632
1668 | -1668
1668 | -1668
1685 | -1685
1709 | -1709
1744 | -1744
1793 | -1793
1817 | -1817
1832 | -1832
1832 | -1832
1849 | -1849
1864.7 | -1864.7
1872.4 | -1872.4
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1877 | -1877
1878 | -1878
1885 | -1885
1885 | -1885
1888 | -1888
1928 | -1928
1957 | -1957
2030 | -2030
2072 | -2072
2115 | -2115
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2155 | -2155
2197 | -2197
2251 | -2251
2310 | -2310
2352 | -2352
2401 | -2401
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2413 | -2413
2427 | -2427
2427 | -2427
2427 | -2427
2427 | -2427
2427 | -2427
2469 | -2469
2508 | -2508
2559 | -2559
2613 | -2613
2633 | -2633
2640 | -2640
2657 | -2657
2657 | -2657
2657 | -2657
2657 | -2657
2700 | -2700
2750 | -2750
2784 | -2784
2823 | -2823
2848 | -2848
2869 | -2869
2901 | -2901
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2911 | -2911
2919 | -2919
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
2919.5 | -2919.5
35 | -35
89 | -89
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
107 | -107
119 | -119
152 | -152
203 | -203
260 | -260
280 | -280
290 | -290
333 | -333
368 | -368
379.5 | -379.5
430 | -430
467 | -467
495 | -495
531 | -531
545 | -545
545 | -545
545 | -545
545 | -545
545 | -545
546 | -546
547.6 | -547.6
594 | -594
681 | -681
758 | -758
805 | -805
851 | -851
903 | -903
916 | -916
994 | -994
1026 | -1026
1026 | -1026
1026 | -1026
1026 | -1026
1026 | -1026
1069 | -1069
1126 | -1126
1171 | -1171
1211 | -1211
1266 | -1266
1327 | -1327
1374 | -1374
1403.4 | -1403.4
1403.4 | -1403.4